## Estimate
PROJECT PROPOSAL ESTIMATE
FROM
Business name | Example Digital Studio
Address | 2 Example Yard, Sampletown
Phone / email | [Phone or email]
ESTIMATE DETAILS
Proposal / estimate no. | PP-2026-019
Date | 20 Oct 2026
Valid until | 19 Nov 2026
Prepared by | [Estimator name]
CLIENT
Client name | Sample Outdoor Gear Ltd
Contact | [Name and email]
PROJECT
Project | Online store rebuild
Objective | Replace the current store with a faster, mobile-friendly site
Proposed start | 16 Nov 2026
Estimated duration | 9 weeks
PHASES AND MILESTONES
Phase / milestone | Days | Day rate | Amount
1. Discovery and requirements workshop | 4 | 720 | 2880
2. Design: page layouts and style guide | 8 | 720 | 5760
3. Build: store setup, product import, integrations | 15 | 720 | 10800
4. Testing, training and launch | 5 | 720 | 3600
5. Post-launch support (first 4 weeks) | 2 | 720 | 1440
Subtotal |  |  | 24480
Sales tax, if applicable |  | 0% | 0
Estimated total |  |  | 24480
Proposed deposit |  | 25% | 6120
TIMELINE
Weeks 1-2: discovery; design starts
Weeks 3-4: design sign-off
Weeks 5-8: build and testing
Week 9: training and launch
ASSUMPTIONS
Client supplies product data and images by the end of week 2
Two rounds of design revisions are included
Third-party costs (hosting, apps, payment processing) are the client's own and are not included
PROPOSED PAYMENT SCHEDULE
Deposit (amount above) on acceptance
40% on design sign-off
35% on launch
Accepted for the client (signature) |  | Print name and title
Date
This proposal and estimate are valid until the date shown above. Changes to scope are estimated separately before work starts.