REMODELING ESTIMATE

| REMODELING CONTRACTOR Business name: Example Renovation Group Address: 410 Example Street, Sampletown Phone / email: [Phone or email] License no.: [License no., if required where you work] | ESTIMATE DETAILS Estimate no.: RM-3104 Date: Nov 10, 2026 Valid until: Jan 8, 2027 Prepared by: [Project manager] |
| --- | --- |

CLIENT AND PROJECT

| Client name | Taylor Example | Phone / email | [Phone or email] |
| --- | --- | --- | --- |
| Project address | 91 Sample Court, Sampletown |  |  |
| Year built | 1994 |  |  |
| Project | Kitchen remodel and opening the wall to the family room |  |  |
| Areas | Kitchen, about 220 sq ft; family room, about 340 sq ft |  |  |
| Estimated duration | 10 to 12 weeks after permits are issued |  |  |

PHASE 1: DEMOLITION AND SITE PROTECTION

| Description | Qty | Unit | Unit price | Amount |
| --- | --- | --- | --- | --- |
| Floor and dust protection for the work area | 1 | lot | 650.00 | 650.00 |
| Remove kitchen cabinets, counters and appliances | 1 | lot | 1,400.00 | 1,400.00 |
| Remove the wall between the kitchen and family room | 14 | lin ft | 85.00 | 1,190.00 |
| Debris hauling and dumpster | 2 | haul | 575.00 | 1,150.00 |
| Demolition subtotal |  |  |  | 4,390.00 |

PHASE 2: FRAMING AND STRUCTURE

| Description | Qty | Unit | Unit price | Amount |
| --- | --- | --- | --- | --- |
| Engineered beam to replace the removed wall, installed | 1 | each | 3,800.00 | 3,800.00 |
| Structural engineering for the beam | 1 | lot | 950.00 | 950.00 |
| Frame the pantry wall and soffit changes | 1 | lot | 1,250.00 | 1,250.00 |
| Framing subtotal |  |  |  | 6,000.00 |

PHASE 3: PLUMBING, ELECTRICAL AND HVAC

| Description | Qty | Unit | Unit price | Amount |
| --- | --- | --- | --- | --- |
| Plumbing: move the sink to the island, new supply and drain lines | 1 | lot | 3,200.00 | 3,200.00 |
| Electrical: new circuits, receptacles and lighting | 1 | lot | 4,600.00 | 4,600.00 |
| HVAC: extend 2 supply ducts and move the return | 1 | lot | 1,350.00 | 1,350.00 |
| Mechanical subtotal |  |  |  | 9,150.00 |

PHASE 4: DRYWALL AND FINISHES

| Description | Qty | Unit | Unit price | Amount |
| --- | --- | --- | --- | --- |
| Drywall, taped and finished | 820 | sq ft | 3.20 | 2,624.00 |
| Install cabinets (cabinets under allowances) | 22 | lin ft | 95.00 | 2,090.00 |
| Install flooring (flooring under allowances) | 560 | sq ft | 4.50 | 2,520.00 |
| Tile backsplash, installed | 45 | sq ft | 28.00 | 1,260.00 |
| Paint walls, ceilings and trim | 1 | lot | 2,800.00 | 2,800.00 |
| Finishes subtotal |  |  |  | 11,294.00 |

ALLOWANCES (OWNER SELECTIONS)

| Description | Qty | Unit | Unit price | Amount |
| --- | --- | --- | --- | --- |
| Allowance: cabinets | 1 | allowance | 14,000.00 | 14,000.00 |
| Allowance: countertops, fabricated and installed | 1 | allowance | 5,500.00 | 5,500.00 |
| Allowance: flooring material | 560 | sq ft | 6.00 | 3,360.00 |
| Allowance: light fixtures | 1 | allowance | 1,200.00 | 1,200.00 |
| Allowance: sink, faucet and plumbing fixtures | 1 | allowance | 900.00 | 900.00 |
| Allowances subtotal |  |  |  | 24,960.00 |

| Subtotal | 55,794.00 |
| --- | --- |
| Contingency (10%) | 5,579.40 |
| Sales tax, if applicable (0%) | 0.00 |
| Estimated total | 61,373.40 |

PROPOSED PAYMENT SCHEDULE

- On signing: a deposit of [amount agreed; check the rules where you work]

- After demolition and the beam are complete: 25% of the estimated total

- After the rough plumbing, electrical and HVAC pass inspection: 25%

- After cabinets and countertops are installed: 25%

- On completion and final walkthrough: the remainder

ALLOWANCES AND CONTINGENCY

- Allowances cover owner-selected items; the final cost is adjusted up or down against the amounts shown

- The contingency covers conditions found once walls and floors are opened. Unused contingency is not charged

EXCLUSIONS

- Permit fees, passed through at cost

- Appliances (owner supplied)

- Testing for or removing hazardous materials

- Work outside the kitchen and family room

| Accepted by (client signature) |  | Print name |
| --- | --- | --- |
| Date |  |  |

Prices are based on the scope shown above and are valid until the date shown. Changes to the scope are priced by written change order.