## Estimate
REMODELING ESTIMATE
REMODELING CONTRACTOR
Business name | Example Renovation Group
Address | 410 Example Street, Sampletown
Phone / email | [Phone or email]
License no. | [License no., if required where you work]
ESTIMATE DETAILS
Estimate no. | RM-3104
Date | Nov 10, 2026
Valid until | Jan 8, 2027
Prepared by | [Project manager]
CLIENT AND PROJECT
Client name | Taylor Example
Phone / email | [Phone or email]
Project address | 91 Sample Court, Sampletown
Year built | 1994
Project | Kitchen remodel and opening the wall to the family room
Areas | Kitchen, about 220 sq ft; family room, about 340 sq ft
Estimated duration | 10 to 12 weeks after permits are issued
PHASE 1: DEMOLITION AND SITE PROTECTION
Description | Qty | Unit | Unit price | Amount
Floor and dust protection for the work area | 1 | lot | 650 | 650
Remove kitchen cabinets, counters and appliances | 1 | lot | 1400 | 1400
Remove the wall between the kitchen and family room | 14 | lin ft | 85 | 1190
Debris hauling and dumpster | 2 | haul | 575 | 1150
Demolition subtotal |  |  |  | 4390
PHASE 2: FRAMING AND STRUCTURE
Description | Qty | Unit | Unit price | Amount
Engineered beam to replace the removed wall, installed | 1 | each | 3800 | 3800
Structural engineering for the beam | 1 | lot | 950 | 950
Frame the pantry wall and soffit changes | 1 | lot | 1250 | 1250
Framing subtotal |  |  |  | 6000
PHASE 3: PLUMBING, ELECTRICAL AND HVAC
Description | Qty | Unit | Unit price | Amount
Plumbing: move the sink to the island, new supply and drain lines | 1 | lot | 3200 | 3200
Electrical: new circuits, receptacles and lighting | 1 | lot | 4600 | 4600
HVAC: extend 2 supply ducts and move the return | 1 | lot | 1350 | 1350
Mechanical subtotal |  |  |  | 9150
PHASE 4: DRYWALL AND FINISHES
Description | Qty | Unit | Unit price | Amount
Drywall, taped and finished | 820 | sq ft | 3.2 | 2624
Install cabinets (cabinets under allowances) | 22 | lin ft | 95 | 2090
Install flooring (flooring under allowances) | 560 | sq ft | 4.5 | 2520
Tile backsplash, installed | 45 | sq ft | 28 | 1260
Paint walls, ceilings and trim | 1 | lot | 2800 | 2800
Finishes subtotal |  |  |  | 11294
ALLOWANCES (OWNER SELECTIONS)
Description | Qty | Unit | Unit price | Amount
Allowance: cabinets | 1 | allowance | 14000 | 14000
Allowance: countertops, fabricated and installed | 1 | allowance | 5500 | 5500
Allowance: flooring material | 560 | sq ft | 6 | 3360
Allowance: light fixtures | 1 | allowance | 1200 | 1200
Allowance: sink, faucet and plumbing fixtures | 1 | allowance | 900 | 900
Allowances subtotal |  |  |  | 24960
Subtotal |  |  |  | 55794
Contingency |  |  | 10% | 5579.4
Sales tax, if applicable |  |  | 0% | 0
Estimated total |  |  |  | 61373.4
PROPOSED PAYMENT SCHEDULE
On signing: a deposit of [amount agreed; check the rules where you work]
After demolition and the beam are complete: 25% of the estimated total
After the rough plumbing, electrical and HVAC pass inspection: 25%
After cabinets and countertops are installed: 25%
On completion and final walkthrough: the remainder
ALLOWANCES AND CONTINGENCY
Allowances cover owner-selected items; the final cost is adjusted up or down against the amounts shown
The contingency covers conditions found once walls and floors are opened. Unused contingency is not charged
EXCLUSIONS
Permit fees, passed through at cost
Appliances (owner supplied)
Testing for or removing hazardous materials
Work outside the kitchen and family room
Accepted by (client signature) |  | Print name
Date
Prices are based on the scope shown above and are valid until the date shown. Changes to the scope are priced by written change order.
Template tip (not printed): To leave out "Contingency" or "Sales tax, if applicable", set the line's rate to 0%. Don't delete these rows: the totals refer to them.