## Invoice
ARCHITECTURAL SERVICES INVOICE
ARCHITECT
Firm name | Example Studio Architects
Address | 9 Example Market Street, Suite 300, Sampletown
Phone / email | [Phone or email]
License no. | [License no., if required where you work]
INVOICE DETAILS
Invoice no. | ARC-2611
Invoice date | Nov 30, 2026
Payment terms | Net 30
Due date | Dec 30, 2026
Billing period | Nov 1-30, 2026
Project no. | P-2611
BILL TO (CLIENT)
Client | Jordan and Sam Example
Address | 4 Sample Hill Road, Sampletown
Email | [Email]
PROJECT
Project | New single-family home, about 2,800 sq ft
Site | 18 Sample Ridge Road, Sampletown
Agreement | [Owner-architect agreement ref. and date]
Basic services fee | 64,000.00, fixed
BASIC SERVICES, FIXED FEE
Phase | Phase fee | % complete | Amount
Schematic design (15% of the fee) | 9600 | 100% | 9600
Design development (20%) | 12800 | 100% | 12800
Construction documents (40%) | 25600 | 60% | 15360
Bidding and permitting (5%) | 3200 | 0% | 0
Construction administration (20%) | 12800 | 0% | 0
Earned to date |  |  | 37760
ADDITIONAL SERVICES, HOURLY
Service | Hours | Rate | Amount
Redesign of the garage wing, requested by the client | 6 | 150 | 900
Site visit with the structural engineer | 3 | 150 | 450
Additional services subtotal |  |  | 1350
REIMBURSABLE EXPENSES, AT COST
Expense | Qty | Unit cost | Amount
Printing and plotting, drawing sets | 2 | 85 | 170
Building permit application fee, advanced for the client | 1 | 640 | 640
Subtotal |  |  | 39110
Reimbursable expenses, at cost |  |  | 810
Total |  |  | 39920
Less: previous invoices |  |  | 22400
Amount due |  |  | 17520
HOW TO PAY
Accepted methods | Bank transfer, ACH or check
Account name | [Account name]
Bank details | [Bank name, account and routing numbers]
Payment reference | Invoice ARC-2611 and project P-2611
FEE NOTES
Basic services are billed as the percentage of each phase fee complete to date, as set out in the agreement.
Previous invoices: ARC-2609 (schematic design, 9,600.00) and ARC-2610 (design development, 12,800.00).
Additional services are billed at 150.00 an hour, as agreed; reimbursable expenses are billed at cost.
Please quote the invoice and project numbers with your payment.
Template tip (not printed): To leave out "Less: previous invoices", set it to 0.00. Don't delete these rows: the totals refer to them.