PROGRESS INVOICE

| CONTRACTOR Business name: Example Builders LLC Address: 500 Example Parkway, Sampletown Phone / email: [Phone or email] License no.: [License no., if required where you work] | INVOICE DETAILS Invoice no.: PB-0606 Invoice date: Dec 1, 2026 Payment terms: Net 30 Due date: Dec 31, 2026 Application no.: 6 Period to: Nov 30, 2026 |
| --- | --- |

BILL TO (OWNER)

| Owner | Example Medical Group LLC | Attention | [Owner's representative] |
| --- | --- | --- | --- |
| Address | 75 Sample Boulevard, Sampletown |  |  |
| Email | [Email] |  |  |

PROJECT AND CONTRACT

| Project | Tenant fit-out, Suite 120 | Contract date | Jun 15, 2026 |
| --- | --- | --- | --- |
| Project address | 200 Sample Avenue, Suite 120, Sampletown |  |  |
| Original contract sum | 248,000.00 | Net change by change orders | 6,500.00 |
| Contract sum to date | 254,500.00 |  |  |

SCHEDULE OF VALUES

| Description of work | Scheduled value | % complete | Previously billed | This period | Completed to date |
| --- | --- | --- | --- | --- | --- |
| General conditions | 18,000.00 | 60% | 7,200.00 | 3,600.00 | 10,800.00 |
| Demolition | 12,500.00 | 100% | 12,500.00 | 0.00 | 12,500.00 |
| Framing and drywall | 46,000.00 | 75% | 23,000.00 | 11,500.00 | 34,500.00 |
| Electrical | 38,000.00 | 50% | 11,400.00 | 7,600.00 | 19,000.00 |
| Plumbing | 24,000.00 | 40% | 4,800.00 | 4,800.00 | 9,600.00 |
| HVAC | 41,000.00 | 45% | 8,200.00 | 10,250.00 | 18,450.00 |
| Doors, frames and hardware | 22,000.00 | 20% | 0.00 | 4,400.00 | 4,400.00 |
| Finishes: paint, flooring and ceilings | 46,500.00 | 10% | 0.00 | 4,650.00 | 4,650.00 |
| Change order 1: added storefront door | 6,500.00 | 50% | 0.00 | 3,250.00 | 3,250.00 |

| Total completed to date | 117,150.00 |
| --- | --- |
| Less: retainage (10%) | 11,715.00 |
| Total earned less retainage | 105,435.00 |
| Less: previous payments | 60,390.00 |
| Amount due | 45,045.00 |

HOW TO PAY

| Accepted methods | Bank transfer, ACH or check | Account name | [Account name] |
| --- | --- | --- | --- |
| Bank details | [Bank name, account and routing numbers] |  |  |
| Payment reference | Invoice PB-0606, application 6 |  |  |

BILLING NOTES

- Work completed this period: 50,050.00, the total of the This period column.

- Retainage is held at 10% of the work completed to date, as set out in the contract (a sample rate).

- Previous payments: applications 1 to 5, 60,390.00 received.

- Change order 1 (added storefront door, 6,500.00) was approved on Oct 8, 2026.

Please quote the invoice and application numbers with your payment.