## Invoice
PROGRESS INVOICE
CONTRACTOR
Business name | Example Builders LLC
Address | 500 Example Parkway, Sampletown
Phone / email | [Phone or email]
License no. | [License no., if required where you work]
INVOICE DETAILS
Invoice no. | PB-0606
Invoice date | Dec 1, 2026
Payment terms | Net 30
Due date | Dec 31, 2026
Application no. | 6
Period to | Nov 30, 2026
BILL TO (OWNER)
Owner | Example Medical Group LLC
Attention | [Owner's representative]
Address | 75 Sample Boulevard, Sampletown
Email | [Email]
PROJECT AND CONTRACT
Project | Tenant fit-out, Suite 120
Project address | 200 Sample Avenue, Suite 120, Sampletown
Contract date | Jun 15, 2026
Original contract sum | 248,000.00
Net change by change orders | 6,500.00
Contract sum to date | 254,500.00
SCHEDULE OF VALUES
Description of work | Scheduled value | % complete | Previously billed | This period | Completed to date
General conditions | 18000 | 60% | 7200 | 3600 | 10800
Demolition | 12500 | 100% | 12500 | 0 | 12500
Framing and drywall | 46000 | 75% | 23000 | 11500 | 34500
Electrical | 38000 | 50% | 11400 | 7600 | 19000
Plumbing | 24000 | 40% | 4800 | 4800 | 9600
HVAC | 41000 | 45% | 8200 | 10250 | 18450
Doors, frames and hardware | 22000 | 20% | 0 | 4400 | 4400
Finishes: paint, flooring and ceilings | 46500 | 10% | 0 | 4650 | 4650
Change order 1: added storefront door | 6500 | 50% | 0 | 3250 | 3250
Total completed to date |  |  |  |  | 117150
Less: retainage |  |  |  | 10% | 11715
Total earned less retainage |  |  |  |  | 105435
Less: previous payments |  |  |  |  | 60390
Amount due |  |  |  |  | 45045
HOW TO PAY
Accepted methods | Bank transfer, ACH or check
Account name | [Account name]
Bank details | [Bank name, account and routing numbers]
Payment reference | Invoice PB-0606, application 6
BILLING NOTES
Work completed this period: 50,050.00, the total of the This period column.
Retainage is held at 10% of the work completed to date, as set out in the contract (a sample rate).
Previous payments: applications 1 to 5, 60,390.00 received.
Change order 1 (added storefront door, 6,500.00) was approved on Oct 8, 2026.
Please quote the invoice and application numbers with your payment.
Template tip (not printed): To leave out "Less: retainage", set its rate to 0%; to leave out "Less: previous payments", set it to 0.00. Don't delete these rows: the totals refer to them. On each line, enter "Scheduled value", "% complete" and "Previously billed"; "Completed to date" and "This period" are formulas.